## sprint 2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner | Tracking in Jira (Y/N)?
1 | 01. Account & Subscription Management | 1.02 | 1.02 Managing customer accounts | Design backend logic for 1.02 Managing customer accounts | 2025-03-26 | 2025-04-08 | 100% | Saransh | Y
2 | 01. Account & Subscription Management | 1.02 | 1.02 Managing customer accounts | Create frontend components for 1.02 Managing customer accounts | 2025-03-26 | 2025-04-08 | 100% | Saransh | Y
3 | 01. Account & Subscription Management | 1.02 | 1.02 Managing customer accounts | Perform integration testing for 1.02 Managing customer accounts module | 2025-03-26 | 2025-04-08 | 100% | Saransh | Y
4 | 01. Account & Subscription Management | 1.02 | 1.02 Managing customer accounts | Implement ET-Ex handling for 1.02 Managing customer accounts | 2025-03-26 | 2025-04-08 | 100% | Saransh | Y
5 | 01. Account & Subscription Management | 1.02 | 1.02 Managing customer accounts | Implement FV handling for 1.02 Managing customer accounts | 2025-03-26 | 2025-04-08 | 100% | Saransh | Y
6 | 01. Account & Subscription Management | 1.02 | 1.02 Managing customer accounts | Implement DDV handling for 1.02 Managing customer accounts | 2025-03-26 | 2025-04-08 | 100% | Saransh | Y
7 | 01. Account & Subscription Management | 1.04 | 1.04 Manage restaurant profiles | Design backend logic for 1.04 Manage restaurant profiles | 2025-03-26 | 2025-04-08 | 100% | Saransh | Y
8 | 01. Account & Subscription Management | 1.04 | 1.04 Manage restaurant profiles | Create frontend components for 1.04 Manage restaurant profiles | 2025-03-26 | 2025-04-08 | 100% | Saransh | Y
9 | 01. Account & Subscription Management | 1.04 | 1.04 Manage restaurant profiles | Perform integration testing for 1.04 Manage restaurant profiles module | 2025-03-26 | 2025-04-08 | 100% | Saransh | Y
10 | 01. Account & Subscription Management | 1.04 | 1.04 Manage restaurant profiles | Implement ET-In handling for 1.04 Manage restaurant profiles | 2025-03-26 | 2025-04-08 | 100% | Saransh | Y
11 | 01. Account & Subscription Management | 1.04 | 1.04 Manage restaurant profiles | Implement FV handling for 1.04 Manage restaurant profiles | 2025-03-26 | 2025-04-08 | 100% | Saransh | Y
12 | 01. Account & Subscription Management | 1.04 | 1.04 Manage restaurant profiles | Implement DDV handling for 1.04 Manage restaurant profiles | 2025-03-26 | 2025-04-08 | 100% | Saransh | Y
13 | 01. Account & Subscription Management | 1.04 | 1.04 Manage restaurant profiles | Implement DF-In handling for 1.04 Manage restaurant profiles | 2025-03-26 | 2025-04-08 | 100% | Saransh | Y
14 | 01. Account & Subscription Management | 1.04 | 1.04 Manage restaurant profiles | Implement DF-Out handling for 1.04 Manage restaurant profiles | 2025-03-26 | 2025-04-08 | 100% | Saransh | Y
15 | 03. Orders & Payments | 3.01 | 3.01 Place order | Design backend logic for 3.01 Place order | 2025-04-09 | 2025-04-11 | 100% | Sandeep | Y
16 | 03. Orders & Payments | 3.01 | 3.01 Place order | Create frontend components for 3.01 Place order | 2025-04-09 | 2025-04-11 | 100% | Sandeep | Y
17 | 03. Orders & Payments | 3.01 | 3.01 Place order | Perform integration testing for 3.01 Place order module | 2025-04-09 | 2025-04-11 | 100% | Sandeep | Y
18 | 03. Orders & Payments | 3.01 | 3.01 Place order | Implement Et-Ex handling for 3.01 Place order | 2025-04-09 | 2025-04-11 | 100% | Sandeep | Y
19 | 03. Orders & Payments | 3.01 | 3.01 Place order | Implement OST handling for 3.01 Place order | 2025-04-09 | 2025-04-11 | 100% | Sandeep | Y
20 | 03. Orders & Payments | 3.01 | 3.01 Place order | Implement CL handling for 3.01 Place order | 2025-04-09 | 2025-04-11 | 100% | Sandeep | Y
21 | 03. Orders & Payments | 3.01 | 3.01 Place order | Add tables to store Orders, Order Items (the menu items in each Order), and Payment information for a particular Order | 2025-04-09 | 2025-04-11 | 100% | Sandeep | Y
22 | 03. Orders & Payments | 3.05 | 3.05 Leave ratings and reviews | Design backend logic for 3.05 leave ratings and reviews | 2025-03-26 | 2025-04-08 | 100% | Sandeep | Y
23 | 03. Orders & Payments | 3.05 | 3.05 Leave ratings and reviews | Create frontend components for 3.05 leave ratings and reviews | 2025-03-26 | 2025-04-08 | 100% | Sandeep | Y
24 | 03. Orders & Payments | 3.05 | 3.05 Leave ratings and reviews | Perform integration testing for 3.05 leave ratings and reviews module | 2025-03-26 | 2025-04-08 | 100% | Sandeep | Y
25 | 03. Orders & Payments | 3.05 | 3.05 Leave ratings and reviews | Implement Et-Ex handling for 3.05 leave ratings and reviews | 2025-03-26 | 2025-04-08 | 100% | Sandeep | Y
26 | 03. Orders & Payments | 3.05 | 3.05 Leave ratings and reviews | Implement FV handling for 3.05 leave ratings and reviews | 2025-03-26 | 2025-04-08 | 100% | Sandeep | Y
27 | 03. Orders & Payments | 3.05 | 3.05 Leave ratings and reviews | Implement DDV handling for 3.05 leave ratings and reviews | 2025-03-26 | 2025-04-08 | 100% | Sandeep | Y
28 | 03. Orders & Payments | 3.05 | 3.05 Leave ratings and reviews | Implement DF-Out handling for 3.05 leave ratings and reviews | 2025-03-26 | 2025-04-08 | 100% | Sandeep | Y
29 | 03. Orders & Payments | 3.05 | 3.05 Leave ratings and reviews | Add restriction to reviews table so user can only review a restaurant (at most) once | 2025-03-26 | 2025-04-08 | 100% | Sandeep | Y
30 | 04. Delivery Management | 4.01 | 4.01 Accept and Reject delivery requests | Design backend logic for 4.01 Accept and Reject delivery requests | 2025-04-09 | 2025-04-12 | 100% | Harsh | Y
31 | 04. Delivery Management | 4.01 | 4.01 Accept and Reject delivery requests | Create frontend components for 4.01 Accept and Reject delivery requests | 2025-04-09 | 2025-04-12 | 100% | Harsh | Y
32 | 04. Delivery Management | 4.01 | 4.01 Accept and Reject delivery requests | Perform integration testing for 4.01 Accept and Reject delivery requests module | 2025-04-09 | 2025-04-12 | 100% | Harsh | Y
33 | 04. Delivery Management | 4.01 | 4.01 Accept and Reject delivery requests | Implement DSTS handling for 4.01 Accept and Reject delivery requests | 2025-04-09 | 2025-04-12 | 100% | Harsh | Y
34 | 04. Delivery Management | 4.01 | 4.01 Accept and Reject delivery requests | Implement OST handling for 4.01 Accept and Reject delivery requests | 2025-04-09 | 2025-04-12 | 100% | Harsh | Y
35 | 04. Delivery Management | 4.01 | 4.01 Accept and Reject delivery requests | Implement Et-Ex handling for 4.01 Accept and Reject delivery requests | 2025-04-09 | 2025-04-12 | 100% | Harsh | Y

## sprint 3
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner | Tracking in Jira (Y/N)?
1 | 02. Restaurant Listings & Reservations | 2.02 | 2.02 Make reservations | Design backend logic for 2.02 Make reservations | 2025-04-15 | 2025-04-24 | 100% | Sumedh | N
2 | 02. Restaurant Listings & Reservations | 2.02 | 2.02 Make reservations | Create frontend components for 2.02 Make reservations | 2025-04-15 | 2025-04-24 | 100% | Sumedh | N
3 | 02. Restaurant Listings & Reservations | 2.02 | 2.02 Make reservations | Perform integration testing for 2.02 Make reservations module | 2025-04-15 | 2025-04-24 | 100% | Sumedh | N
4 | 02. Restaurant Listings & Reservations | 2.02 | 2.02 Make reservations | Implement Et-Ex handling for 2.02 Make reservations | 2025-04-15 | 2025-04-24 | 100% | Grishma | N
5 | 02. Restaurant Listings & Reservations | 2.02 | 2.02 Make reservations | Create database tables to store restaurant reservations | 2025-04-15 | 2025-04-24 | 100% | Grishma | Y
6 | 02. Restaurant Listings & Reservations | 2.02 | 2.02 Make reservations | Implement CC handling for 2.02 Make reservations | 2025-04-15 | 2025-04-24 | 100% | Grishma | N
7 | 02. Restaurant Listings & Reservations | 2.03 | 2.03 Manage reservations | Design backend logic for 2.03 Manage reservations | 2025-04-20 | 2025-04-25 | 100% | Harsh | N
8 | 02. Restaurant Listings & Reservations | 2.03 | 2.03 Manage reservations | Create frontend components for 2.03 Manage reservations | 2025-04-20 | 2025-04-25 | 100% | Harsh | N
9 | 02. Restaurant Listings & Reservations | 2.03 | 2.03 Manage reservations | Add code to automatically email/notify the user when their reservation in the database has been modified, cancelled, or confirmed | 2025-04-20 | 2025-04-25 | 100% | Harsh | Y
10 | 02. Restaurant Listings & Reservations | 2.03 | 2.03 Manage reservations | Implement Et-Ex handling for 2.03 Manage reservations | 2025-04-20 | 2025-04-25 | 100% | Harsh | N
11 | 02. Restaurant Listings & Reservations | 2.03 | 2.03 Manage reservations | Implement FV handling for 2.03 Manage reservations | 2025-04-20 | 2025-04-25 | 100% | sandeep | N
12 | 02. Restaurant Listings & Reservations | 2.03 | 2.03 Manage reservations | Implement CC handling for 2.03 Manage reservations | 2025-04-20 | 2025-04-25 | 100% | sandeep | N
13 | 02. Restaurant Listings & Reservations | 2.03 | 2.03 Manage reservations | Produce Test Design Specification | 2025-04-23 | 2025-04-29 | 100% | sandeep | N
14 | 02. Restaurant Listings & Reservations | 2.03 | 2.03 Manage reservations | Produce Test Case Specification | 2025-04-23 | 2025-04-29 | 100% | saransh | N
15 | 02. Restaurant Listings & Reservations | 2.04 | 2.04 Manage table availability | Design backend logic for 2.04 Manage table availability | 2025-04-17 | 2025-04-26 | 100% | saransh | N
16 | 02. Restaurant Listings & Reservations | 2.04 | 2.04 Manage table availability | Create frontend components for 2.04 Manage table availability | 2025-04-17 | 2025-04-26 | 100% | saransh | N
17 | 02. Restaurant Listings & Reservations | 2.04 | 2.04 Manage table availability | Perform integration testing for 2.04 Manage table availability module | 2025-04-17 | 2025-04-26 | 100% | Andrew | N
18 | 02. Restaurant Listings & Reservations | 2.04 | 2.04 Manage table availability | Implement Et-In handling for 2.04 Manage table availability | 2025-04-17 | 2025-04-26 | 100% | Andrew | N
19 | 02. Restaurant Listings & Reservations | 2.04 | 2.04 Manage table availability | Implement FV handling for 2.04 Manage table availability | 2025-04-17 | 2025-04-26 | 100% | Andrew | N
20 | 02. Restaurant Listings & Reservations | 2.04 | 2.04 Manage table availability | Implement DDV handling for 2.04 Manage table availability | 2025-04-17 | 2025-04-26 | 100% | Andrew | N
21 | 02. Restaurant Listings & Reservations | 2.04 | 2.04 Manage table availability | Implement DDD handling for 2.04 Manage table availability | 2025-04-17 | 2025-04-26 | 100% | Andrew | N
22 | 02. Restaurant Listings & Reservations | 2.06 | 2.06 Receive booking & confirmation notification | Design backend logic for 2.06 Receive booking & confirmation notification | 2025-04-20 | 2025-04-26 | 100% | jackie | N
23 | 02. Restaurant Listings & Reservations | 2.06 | 2.06 Receive booking & confirmation notification | Create frontend components for 2.06 Receive booking & confirmation notification | 2025-04-20 | 2025-04-26 | 100% | jackie | N
24 | 02. Restaurant Listings & Reservations | 2.06 | 2.06 Receive booking & confirmation notification | Perform integration testing for 2.06 Receive booking & confirmation notification module | 2025-04-20 | 2025-04-26 | 100% | jackie | N
25 | 02. Restaurant Listings & Reservations | 2.06 | 2.06 Receive booking & confirmation notification | Implement Et-Ex handling for 2.06 Receive booking & confirmation notification | 2025-04-20 | 2025-04-26 | 100% | jackie | N
26 | 02. Restaurant Listings & Reservations | 2.06 | 2.06 Receive booking & confirmation notification | Implement FV handling for 2.06 Receive booking & confirmation notification | 2025-04-20 | 2025-04-26 | 100% | kiran R | N
27 | 03. Orders & Payments | 3.02 | 3.02 Track orders | Design backend logic for 3.02 Track orders | 2025-04-13 | 2025-04-20 | 100% | kiran R | N
28 | 03. Orders & Payments | 3.02 | 3.02 Track orders | Create frontend components for 3.02 Track orders | 2025-04-13 | 2025-04-20 | 100% | jackie | N
29 | 03. Orders & Payments | 3.02 | 3.02 Track orders | Perform integration testing for 3.02 Track orders module | 2025-04-13 | 2025-04-20 | 100% | Grishma | N
30 | 03. Orders & Payments | 3.02 | 3.02 Track orders | Implement Et-Ex handling for 3.02 Track orders | 2025-04-13 | 2025-04-20 | 100% | Grishma | N
31 | 03. Orders & Payments | 3.02 | 3.02 Track orders | Implement OST handling for 3.02 Track orders | 2025-04-13 | 2025-04-20 | 100% | Grishma | N
32 | 03. Orders & Payments | 3.02 | 3.02 Track orders | Implement DSTS handling for 3.02 Track orders | 2025-04-13 | 2025-04-20 | 100% | kiran R | N
33 | 03. Orders & Payments | 3.02 | 3.02 Track orders | Produce Test Design Specification | 2025-04-23 | 2025-04-29 | 100% | kiran R | N
34 | 03. Orders & Payments | 3.02 | 3.02 Track orders | Produce Test Case Specification | 2025-04-23 | 2025-04-29 | 100% | kiran R | N
35 | 04. Delivery Management | 4.05 | 4.05 Update order status | Design backend logic for 4.05 update order status | 2025-04-13 | 2025-04-20 | 100% | Akshata | N
36 | 04. Delivery Management | 4.05 | 4.05 Update order status | Create frontend components for 4.05 update order status | 2025-04-13 | 2025-04-20 | 100% | Akshata | N
37 | 04. Delivery Management | 4.05 | 4.05 Update order status | Perform integration testing for 4.05 update order status module | 2025-04-13 | 2025-04-20 | 100% | Akshata | N
38 | 04. Delivery Management | 4.05 | 4.05 Update order status | Implement Et-In handling for 4.05 update order status | 2025-04-13 | 2025-04-20 | 100% | Akshata | N
39 | 04. Delivery Management | 4.05 | 4.05 Update order status | Implement Et-Ex handling for 4.05 update order status | 2025-04-13 | 2025-04-20 | 100% | Akshata | N
40 | 04. Delivery Management | 4.05 | 4.05 Update order status | Implement OST handling for 4.05 update order status | 2025-04-13 | 2025-04-20 | 100% | Akshata | N
41 | 04. Delivery Management | 4.05 | 4.05 Update order status | Implement DSTS handling for 4.05 update order status | 2025-04-13 | 2025-04-20 | 100% | kiran V | N
42 | 04. Delivery Management | 4.05 | 4.05 Update order status | Produce Test Design Specification | 2025-04-23 | 2025-04-29 | 100% | kiran V | N
43 | 04. Delivery Management | 4.05 | 4.05 Update order status | Produce Test Case Specification | 2025-04-23 | 2025-04-29 | 100% | kiran V | N