## Sheet1
Module | Title | As a/an | I want to.. | So that I Can | Sprint | Story Points | story Constraints | Story Exceptions
01. Account & Subscription Management | 01.01 Create customer accounts | Customer, Admin | Create an account to access the platform | Use platform services like ordering, reservations, and subscriptions | 1 | 2 | Only Subscribed Customers and Admins can create accounts; email/phone validation required. | If the email/phone format is invalid or the username already exists, account creation will fail.
| 01.02 Manage customer accounts | Customer, Admin | Update my profile information | Keep my details accurate and up to date | 2 | 3 | Only Subscribed Customers and Admins can update profiles; changes must be logged. | If required fields (e.g., email, contact details) are incomplete or incorrectly formatted, updates will fail.
| 01.03 Create restaurant profiles | Restaurant owner, Admin | Register my restaurant | List my restaurant on the platform to accept orders and reservations | 1 | 4 | Only Restaurant Owners and Admins can create profiles; profile verification required. | If duplicate or fraudulent profiles are detected, creation will be blocked.
| 01.04 Manage restaurant profiles | Restaurant owner, Admin | Update my restaurant’s details | Keep my business information up to date for customers | 1 | 4 | Only Restaurant Owners and Admins can update profiles; admin approval required for changes. | If unauthorized modifications are attempted, changes will be prevented.
| 01.05 Handle account suspensions & reactivations | Admin | Suspend or reactivate accounts | Enforce platform policies and prevent misuse | TBH |  | Only Admins can suspend/reactivate accounts; users must be notified. | If accidental suspensions occur, manual reversal may be required.
| 01.06 Secure login | User, Admin | Log in securely using my credentials | Prevent unauthorized access to my account | 1 | 5 | Only Subscribed Customers, Restaurant Owners, and Admins can log in; MFA and encryption required. | If incorrect password attempts exceed the limit, users may be locked out.
| 01.07 Track customer & restaurant account history | Admin, Restaurant owner | Track account activity for security and auditing | Maintain security, compliance, and fraud detection | TBH |  | Only Admins and Restaurant Owners can track history; data retention policies must be followed. | If data privacy regulations are violated, access may be restricted.
| 01.08 Manage subscriptions & upgrades | Customer, Admin | Manage my subscription plan and upgrade if needed | Access premium features and services | TBH |  | Only Subscribed Customers and Admins can manage subscriptions; payments must be secure. | If subscription downgrades occur, data loss may happen.
02. Restaurant Listings & Reservations | 02.01 Search & filter | Customer, Guest | Search and filter restaurants | Quickly find the best dining options based on preferences | 1 | 3 | Only Subscribed Customers and Guests can search; search algorithms must be optimized. | If there is poor connectivity or high traffic, search results may be delayed.
| 02.02 Make reservations | Customer | Book a table at a restaurant | Secure my preferred dining time | 3 | 4 | Only Subscribed Customers can make reservations; real-time availability required. | If double bookings occur, reservations may fail.
| 02.03 Manage reservations | Restaurant owner, Admin | Modify, cancel, or confirm reservations | Keep bookings up to date and avoid overbooking | 3 | 3 | Only Restaurant Owners and Admins can manage reservations; users must be notified of changes. | If last-minute cancellations occur, restaurant operations may be impacted.
| 02.04 Manage table availability | Restaurant owner, Admin | Update table availability in real-time | Ensure customers can book available tables | 3 | 3 | Only Restaurant Owners and Admins can update availability; changes must reflect instantly. | If system delays occur, overbooking may happen.
| 02.05 Access sales & business reports | Restaurant owner, Admin | View reports to analyze my business performance | Make informed business decisions | TBH |  | Only Restaurant Owners and Admins can access reports; reports must be updated daily. | If data inaccuracies occur, decision-making may be affected.
| 02.06 Receive booking & confirmation notification | Customer, Restaurant Owner | Get notified when a reservation is booked or confirmed | Stay informed about booking status | 3 | 2 | Only Subscribed Customers and Restaurant Owners can receive notifications; notifications must be instant. | If notifications are delayed, confusion may arise.
| 02.07 View restaurant details, menu, and reviews | Customer, Guest | Explore restaurant details before making a choice | Choose the best option based on food, price, and reviews | 1 | 2 | Only Subscribed Customers and Guests can view details; data must be up-to-date. | If fake reviews are posted, they may appear in the results.
| 02.08 Promote offers & loyalty program | Restaurant owner, Admin | Manage promotional deals and loyalty rewards | Attract more customers and encourage repeat visits | TBH |  | Only Restaurant Owners and Admins can manage promotions; discounts must be validated. | If fraudulent use of offers occurs, promotions may be misused.
| 02.09 Track restaurant performance | Restaurant owner, Admin | Monitor my restaurant's key metrics and performance | Improve operations and identify trends | TBH |  | Only Restaurant Owners and Admins can track performance; metrics must be accurate and real-time. | If data is misreported, performance tracking may be inaccurate.
03. Orders & Payments | 03.01 Place orders | Customer, Guest | Place an order for food delivery | Receive meals conveniently at my location | 2 | 3 | Only Subscribed Customers and Guests can place orders; order data must be validated. | If payment fails, order confirmation may not occur.
| 03.02 Track orders | Customer, Guest | Pay for my order securely | Stay informed about estimated delivery time | 3 | 3 | Only Subscribed Customers and Guests can track orders; real-time tracking required. | If connectivity issues occur, tracking updates may be delayed.
| 03.03 Manage refunds & disputes | Customer, Restaurant Owner, Admin | Request, review, and process refunds or disputes | Ensure fair resolution of payment issues | TBH |  | Only Admins and Restaurant Owners can process refunds; platform policies must be followed. | If fraudulent refund requests occur, disputes may arise.
| 03.04 Oversee subscription & commission payments | Admin, Restaurant owner | Track and manage payments for subscriptions and commissions | Ensure accurate financial transactions | TBH |  | Only Admins and Restaurant Owners can oversee payments; transactions must be logged. | If payment delays occur, transactions may be incomplete.
| 03.05 Leave ratings & reviews | Customes | Leave feedback and rate my experience | Help others make informed choices | 2 | 2 | Only Subscribed Customers can leave reviews; reviews must be moderated. | If fake reviews are submitted, they may appear on the platform.
| 03.06 Make secure payments | Customer, Guest | Ensure my payment transactions are secure | Prevent fraud and unauthorized transactions | TBH |  | Only Subscribed Customers and Guests can make payments; encryption and secure gateways required. | If payment details are incorrect, transactions may fail.
| 03.07 Process payments between parties | Admin, Payment Processor | Facilitate secure transactions between customers and restaurants | Ensure smooth financial operations | TBH |  | Only Admins and Payment Processors can facilitate transactions; payment logs must be maintained. | If disputes occur, manual intervention may be required.
| 03.08 Generate financial reports | Restaurant owner, Admin | Generate financial summaries for business insights | Keep track of earnings and expenses | TBH |  | Only Admins and Restaurant Owners can generate reports; reports must be exportable. | If data is incorrect, reports may be flagged.
| 03.09 Redeem offers | Customer | Apply discounts and special offers to my orders | Save money on my purchases and enjoy exclusive deals | TBH |  | Only Subscribed Customers can redeem offers; offer eligibility must be validated. | If offer conditions are not met, redemption may fail.
| 03.10 Earn loyalty points | Customer | Accumulate points for future rewards | Earn rewards for continued use of the platform | TBH |  | Only Subscribed Customers can earn points; points must be accumulated correctly. | If campaigns exclude points, users may not earn rewards.
04. Delivery Management | 04.01 Accept & reject delivery requests | Delivery Partner, Admin | Accept or decline delivery tasks | Ensure efficient delivery management by accepting relevant tasks | 2 | 4 | Only Delivery Partners and Admins can manage requests; notifications must be sent promptly. | If delivery partners are unavailable, requests may be rejected.
| 04.02 Track earnings & tips | Delivery Partner | Monitor my earnings and received tips | Track how much I have earned during deliveries | TBH |  | Only Delivery Partners can track earnings; earnings must be updated after each task | If system lag occurs, earnings may be delayed.
| 04.03 Monitor delivery partner performance | Admin | Track delivery partners' performance metrics | Assess how well delivery partners are performing in terms of time, accuracy, and customer satisfaction | TBH |  | Only Admins can monitor performance; key metrics like delivery time must be tracked.Only Admins can monitor performance; key metrics like delivery time must be tracked. | If data is manipulated, performance metrics may be inaccurate.
| 04.04 Assign & reassign delivery tasks | Admin | Manage and reassign delivery orders | Ensure tasks are reassigned to delivery partners when needed for better distribution of workload | TBH |  | Only Admins can assign tasks; reassignments must be based on availability. | If partners are unavailable, reassignments may fail.
| 04.05 Update order status | Delivery Partner, Restaurant Owner | Update the status of an order in real-time | Provide accurate, up-to-date information for both customers and restaurant owners | 3 | 2 | Only Delivery Partners and Restaurant Owners can update status; updates must be in sync with delivery progress. | If updates are delayed, customers may be confused
| 04.06 Provide safety support | Admin | Ensure safety measures and emergency support for delivery partners | Provide peace of mind to delivery partners with support in case of emergency or safety concern | TBH |  | Only Admins can provide safety support; emergency support must be available. | If manual intervention is required, support may be delayed.
| 04.07 Analyze delivery data for improvement | Admin | Analyze delivery data for optimization and better efficiency | Identify areas of improvement in the delivery process to reduce delays and improve service quality | TBH |  | Only Admins can analyze data; data must include delivery times and customer feedback. | If data volume is high, processing may take longer.
| 04.08 Resolve delivery disputes | Customer, Admin | Resolve disputes regarding delivery issues | Ensure customer satisfaction by addressing complaints and resolving disputes promptly | TBH |  | Only Admins can resolve disputes; disputes must be resolved within a set timeframe. | If legal intervention is required, disputes may take longer to resolve.
05. Advertisement Management | 05.01 Manage restaurant ads | Restaurant owner, Admin | Create and manage ads for my restaurant | Promote my restaurant through targeted advertising | TBH |  | Only Restaurant Owners can manage ads; ads must follow platform guidelines. | If ads underperform, they may need to be removed or modified.
| 05.02 Manage delivery partner ads | Admin | Manage advertisements targeted at delivery partners | Promote opportunities or benefits for delivery partners | TBH |  | Only Admins can manage ads; ads must be targeted based on partner preferences. | If partners opt out, ads may not be delivered.
| 05.03 Analyze market trends | Admin | Analyze trends for better marketing strategies | Identify key trends in the market that can inform ad strategies | TBH |  | Only Admins can analyze trends; historical and real-time data must be used. | If third-party tools are required, insights may be delayed.
| 05.04 Create advertisements | Admin, Restaurant owner | Create promotional content for my restaurant | Advertise my restaurant's deals and promotions | TBH |  | Only Admins and Restaurant Owners can create ads; ads must align with platform standards. | If content quality is low, ads may require approval.
| 05.05 Edit advertisements | Admin, Restaurant owner | Update and modify ad content | Keep ads fresh and relevant by updating content regularly | TBH |  | Only Admins and Restaurant Owners can edit ads; edits must be reviewed and approved. | If updates are not automatic, manual intervention may be required.
| 05.06 Remove advertisements | Admin | Remove ads when they are no longer relevant | Keep the platform free from outdated or irrelevant ads | TBH |  | Only Admins can remove ads; ads must be removed promptly when irrelevant. | If removal is delayed, users may see outdated ads.
| 05.07 Generate ad performance reports | Admin | Evaluate how well my ads are performing | Assess ad performance to understand the return on investment (ROI) | TBH |  | Only Admins can generate reports; reports must include key metrics like click-through rates. | If system delays occur, data may be incomplete.
06. Customer Support | 06.01 Chat with customers/restaurants for issue resolution | Customer, Restaurant Owner, Admin | Communicate for issue resolution | Address and resolve issues in real-time with direct communication | TBH |  | Only Admins and Customer Support can initiate chats; must support text and attachments. | If follow-up actions are required, issues may not be resolved immediately.
| 06.02 View customer queries | Admin | Track and manage user queries | Resolve user issues efficiently by viewing their submitted queries | TBH |  | Only Admins can view queries; queries must be filtered and categorized. | If escalation is required, queries may take longer to resolve.
| 06.03 Update customer queries | Admin | Provide updates and resolutions to customer inquiries | Ensure that customers are informed about the status of their queries | TBH |  | Only Admins can update queries; a record of queries must be maintained. | If updates are delayed, customers may become frustrated.
| 06.04 Track subscription & user trends | Admin | Monitor trends related to subscriptions and user engagement | Understand customer behavior to make data-driven decisions | TBH |  | Only Admins can track trends; trends must be analyzed using analytics. | If trends are unclear, further research may be required.
| 06.05 Generate support tickets | Customer, Restaurant owner | Create support tickets for assistance | Receive help with my concerns and ensure timely resolution | TBH |  | Only Subscribed Customers and Restaurant Owners can generate tickets; tickets must be categorized by priority. | If issues are outside platform capabilities, tickets may not be resolved.
| 06.06 Escalate support tickets | Admin | Escalate critical support issues | Ensure urgent or complex issues are handled by senior support teams | TBH |  | Only Admins can escalate tickets; escalation procedures must be followed. | If tickets are complex, they may require multiple escalations.
| 06.07 Notify users when issues are resolved | Admin | Send notifications when support tickets are resolved | Keep users informed about the status of their issues and solutions | TBH |  | Only Admins can send notifications; notifications must include resolution details. | If new problems arise, issues may not be fully resolved.