## Road Map
DineDash
|  |  | SPRINT 1 | SPRINT 2 | SPRINT 3
Application Modules | Feature Backlog | Story Points | SPRINT1 - 03/25/2025 | SPRINT2 - 04/15/2025 | SPRINT3 - 05/06/2025
01. Account & Subscription Management | 01.01 Create customer accounts | 2 | X
| 01.02 Manage customer accounts | 3 |  | X
| 01.03 Create restaurant profiles | 4 | X
| 01.04 Manage restaurant profiles | 4 |  | X
01.05 Handle account suspensions & reactivations
| 01.06 Secure login | 5 | X
01.07 Track customer & restaurant account history
01.08 Manage subscriptions & upgrades
02. Restaurant Listings & Reservations | 02.01 Search & filter | 3 | X
| 02.02 Make reservations | 4 |  |  | X
| 02.03 Manage reservations | 3 |  |  | X
| 02.04 Manage table availability | 3 |  |  | X
02.05 Access sales & business reports
| 02.06 Receive booking & confirmation notification | 2 |  |  | X
| 02.07 View restaurant details, menu, and reviews | 2 | X
02.08 Promote offers & loyalty program
02.09 Track restaurant performance
03. Orders & Payments | 03.01 Place orders | 3 |  | X
| 03.02 Track orders | 3 |  |  | X
03.03 Manage refunds & disputes
03.04 Oversee subscription & commission payments
| 03.05 Leave ratings & reviews | 2 |  | X
03.06 Make secure payments
03.07 Process payments between parties
03.08 Generate financial reports
03.09 Redeem offers
03.10 Earn loyalty points
04. Delivery Management | 04.01 Accept & reject delivery requests | 4 |  | X
04.02 Track earnings & tips
04.03 Monitor delivery partner performance
04.04 Assign & reassign delivery tasks
| 04.05 Update order status | 2 |  |  | X
04.06 Provide safety support
04.07 Analyze delivery data for improvement
04.08 Resolve delivery disputes
05. Advertisement Management | 05.01 Manage restaurant ads
05.02 Manage delivery partner ads
05.03 Analyze market trends
05.04 Create advertisements
05.05 Edit advertisements
05.06 Remove advertisements
05.07 Generate ad performance reports
06. Customer Support | 06.01 Chat with customers/restaurants for issue resolution
06.02 View customer queries
06.03 Update customer queries
06.04 Track subscription & user trends
06.05 Generate support tickets
06.06 Escalate support tickets
06.07 Notify users when issues are resolved
|  | VELOCITY : | 16 | 16 | 17

## Jira Road Map
Timeline/Roadmap View: Months
Timeline/Roadmap View: Weeks
Kanban Board

## Kanban Board 1
Updated Kanban Board

## Kanban board sprint2
Updated kanaban sprint 2

## Updated kanban board sprint 2
Updated kanban board Sprint 2

## kanban sprint2 final
Kanban Sprint 2 Final

## Critical tasks sprint 3
Sprint3 with updated critical tasks

## Sprint 3 updated
Updated sprint 3